## Time Plan
The time chart below updates automatically based on Start and End dates, and the "Show from" date. Do not enter anything manually here.
|  |  | Project start | 2024-03-01 |  |  | wk 9 | [6 empty] | wk 10 | [6 empty] | wk 11 | [6 empty] | wk 12 | [6 empty] | wk 13 | [6 empty] | wk 14 | [6 empty] | wk 15 | [6 empty] | wk 16 | [6 empty] | wk 17 | [6 empty] | wk 18 | [6 empty] | wk 19 | [6 empty] | wk 20 | [6 empty] | wk 21 | [6 empty] | wk 22 | [6 empty] | wk 23 | [6 empty] | wk 24
|  |  | Show from | 2024-03-01 |  |  | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29 | [6 empty] | 2024-05-06 | [6 empty] | 2024-05-13 | [6 empty] | 2024-05-20 | [6 empty] | 2024-05-27 | [6 empty] | 2024-06-03 | [6 empty] | 2024-06-10
|  |  | Updated at | 2024-01-01 | time axis 2024-02-26 to 2024-06-17
STATUS | WHAT | WHO | DONE | START | END | DAYS | time axis 2024-02-26 to 2024-06-17
0 | Initiating Phase (4 activitites)
0 | Project Outline - Completed and Signed | EasyFill/Customer | 0% | 2024-03-01 | 2024-03-01
0 | Select Test Store | Customer | 0% | 2024-03-01 | 2024-03-08
0 | Complete Initial Time Plan | EasyFill/Customer | 0% | 2024-03-01 | 2024-03-01
0 | Gather Contact Person Information in Time Plan document | Customer | 0% | 2024-03-08 | 2024-03-08
0 | Planning Phase (2 activitites)
0 | Test Area and Product Categories | Customer | 0% | 2024-03-08 | 2024-03-15 | 8
0 | Existing Gondola System Measurements | Customer | 0% | 2024-03-15 | 2024-03-18 | 4
0 | Planning for retrofit installation | EasyFill | 0% | 2024-03-18 | 2024-03-25
0 | Planogram Management training session | EasyFill/Customer | 0% | 2024-03-15 | 2024-03-15
0 | Planogram Planning | Customer | 0% | 2024-03-18 | 2024-03-25
0 | Installation Phase (0 activitites)
| Installation project activities |  | 0%
0 | Test Phase (0 activitites)
0 | Measure "Before" | Customer | 0% | 2024-03-15 | 2024-03-25
0 | Test | Customer | 0% | 2024-03-26 | 2024-06-18 | 85
0 | Start Survey | EasyFill/Customer | 0% | 2024-04-02 | 2024-04-02 | 1
0 | Mid Survey | EasyFill/Customer | 0% | 2024-04-23 | 2024-04-23 | 1
0 | End Survey | EasyFill/Customer | 0% | 2024-06-11 | 2024-06-11
0 | Evaluation (2 activitites) | -Rubrik-
0 | Hand over measurement and statistics to EasyFill | Customer | 0% | 2024-06-18 | 2024-06-18 | 1
0 | Evaluation meeting and Next Step | EasyFill/Customer | 0% | 2024-06-21 | 2024-06-21 | 1
Insert new rows ABOVE this one | bar: 2024-06-17
Note on G4: This date controls the start of the time chart to the right.
Note on C6: Put a number in column C to indicate status of an activity. 0: Grey (no status) 1: Red 2: Yellow 3: Green
Note on J6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## Contacts
EasyFill | Name | Email | Phone
Main Contact | Oliver Eischeid | oliver.eischeid@easyfill.eu | +49 (0)175 480 82 92
Customer | Name | Email | Phone
Main Contact
Store Manager
Planogram Management
On-site technical person
Billing Information
VAT
Address
Test Location
Phone number
Address

## About (hidden)
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.